## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Garcia | 2026-02-06 | Unused imports not detected correctly | Sprint 1 | Self | Logical | Fixed detection logic | 2026-02-07 | Closed | Working properly
2 | Garcia | 2026-02-07 | Input code not accepting some formats | Sprint 1 | Self | Functional | Handled input properly | 2026-02-07 | Closed | Issue fixed
3 | Garcia | 2026-02-10 | Undefined variables not flagged | Sprint 2 | Self | Logical | Improved validation | 2026-02-11 | Closed | Resolved
4 | Garcia | 2026-02-13 | PEP8 rules not applied correctly | Sprint 3 | Self | Standards | Updated checks | 2026-02-14 | Closed | Improved output
5 | Garcia | 2026-02-18 | Output UI not clear | Sprint 4 | Self | UI | Improved display | 2026-02-19 | Closed | Clear now
6 | Garcia | 2026-02-23 | AI suggestions not accurate | Sprint 5 | Self | Logical | Refined prompts | 2026-02-23 | Closed | Better results

## Sheet2
Logical
User Interface
Maintainability
Standards
Others